## DefectSummary
Defect Id | Issue | Description | Status | severity | Assigned to | Comments
Defect1 | Password policy not matching with Acceptance criteria. | According to the acceptance Criteria from the user story,password policy criteria is minimum 8 characters (1 uppercase + 1 lowercase + 1 special character).While Registering the visitor information, Entered a password with an uppercase +lowercase+ special character Example: Adam@!#. But Page throwing an excpetion as below. <password did not conform wth policy, password must have numeric characters> enter numeric character. This is conflicting from the user story requirement. | Pending | medium
Defect2 | After Login still page showing the Registration page . | Entered vistor registration information and didn't registered. Login with another user login. After login still page showing the Registration page with the entered inforamtion. | Pending | high
Defect3 | System allowing invalid phone number. | 3. Login with the visitor user name and password and clicked on the profile tab. system allowing more than required digits in phone number field. Entered in phone number field as below --> 49830498039094034545545455454545454545545940584954343434344343434 | Pending | high
Defect4 | Refresh Issue: After logout, still can see the profile page details. | Login with credentials and click on profile page tab to view the information. Then logout from the application. Still page showing the previous login user profile details. This is a user privacy voilation. | Pending | high
Defect5 | Can Register duplicate user logins(login user id should not be case sensitive) | Able to register with lowercase and uppercase login user ids with same name as below. Example data: Registed with testmyapp as user id. Registed with TESTMYAPP as user id. System Allowed to created both users. | Pending | mediuum |  | This could be specific to requirement for the application, As most of the login user name is not case sensitive. And in the user story it is not mentioned that login is case sensitive.
Defect6 | Profile Page-Typo error in password change tab. | Change Password tab --> New Password field prompt have a type error as New pasword | Pending | low
Defect7 | Profile Page- Irrelavant Error message is displaying while changing the password | Logged in As a visitor and click on profile page. Enter new password and confirm password without current password.System throwing Invalid error message as below. InvalidParameter: 1 validation error(s) found. - minimum field size of 6, ChangePasswordInput.PreviousPassword. It should display a valid message to prompt the user as below. Enter current password and change the password. | Pending | medium
Defect8 | Invalid help text in Register page | Register page, while Registering the visitor didn't enter the last name, system prompting as First name is required. It should be Last name is required. | pending | low

## Defect1
1

## Defect2
2. Page not refreshing

## Defect3
3. Profile Page --> Invalid phone number, New Password prompt wrong spelling.

## Defect4
4. After logout, still can see the profile page details.

## Defect5
5. Can create the duplicate users with case sensitive
Can register with TESTMYAPP/testmyapp as two different users. Login name always should be unique.

## Defect6
6. New pasword is displaying instead of New password